## Description
Event Name | Date Start | Date End | Test Type | Description
Developmental Test Phase 2 | 2012-08-06 | 2013-11-15 | Developmental | Testing was done with the objective of satisfying the IOT&E entrance criteria as well as test requirements outlined the approve Test and Evaluation Master Plan. Results of testing were used to assess the systems readiness to conduct the Initial Operational Test and Evaluation as well as the [REDACTED].

## Testing Subsets
Test Data Evaluated | Result | Result Notes
Reliability Growth Demonstrations | Satisfactory
Performance Testing | Satisfactory
Software Independent Validation and Verification (IV&V) | Satisfactory
Logistics Demonstration (LD) and Prognostics/Diagnostics Demonstration | Satisfactory
Logistics Demonstration Phase 2 | Satisfactory
Electromagnetic Interference (EMI)/ Electromagnetic Compatibility (EMC)/ Electromagnetic Environmental Effects (E3) | Satisfactory
Nuclear, Biological, Chemical Contamination Survivability (NBCCS) | Satisfactory
Electronic Warfare (EW) Survivability | Satisfactory
Transportability/Mobility | Satisfactory

## Key
Test Data
Electronic Warfare (EW) Survivability
Electromagnetic Interference (EMI)/ Electromagnetic Compatibility (EMC)/ Electromagnetic Environmental Effects (E3)
Environmental Testing
Transportability/Mobility
Reliability Growth Demonstrations
Nuclear, Biological, Chemical Contamination Survivability (NBCCS)
Performance Testing
Army Interoperability Certification (AIC) Testing
Logistics Demonstration (LD) and Prognostics/Diagnostics Demonstration
Technical Publication Verification
Manpower and Personnel Integration (MANPRINT) Analysis Conference (MAC)
Software Qualification Test (SQT)
Software Independent Validation and Verification (IV&V)
Model and Simulation Verification
Logistics Demonstration Phase 2
Radar Mode Characterization Test
Cyber Security