## Description
Event Name | Date Start | Date End | Test Type | Description
Initial Operational Test and Evaluation 1 | 2014-03-24 | 2014-05-18 | Operational | Test was executed using four production-representative LRIP assets. In addition to the 4 systems under test, PdM Radars provided one spare SUT. The IOT evaluated the effectiveness, suitability and survivability of a unit equipped with the SUT while providing a forward deployed, self-supported ground force Counterfire capability to effectively detect and locate enemy mortars, cannon, and rocket firing locations.

## Testing Subsets
Test Data Evaluated | Result | Result Notes
Performance Testing | Satisfactory
Manpower and Personnel Integration (MANPRINT) Analysis Conference (MAC) | Issue | Data was collected during the IOT for a qualitative MANPRINT and Human Factors Engineering evaluation consisting of on-site observation, data collection, and interviews of Target Audience Soldiers that employed and operated the AN/TPQ-53 during the IOT. Soldier questionnaires were administered immediately following IOT training, the Pilot and Record Test events culminating with final interviews and an Exit Questionnaire at IOT ENDEX, before the Soldiers under test departed the test range to return to their home stations.
Logistics Demonstration Phase 2 | Satisfactory | The delta Logistics Demonstration Phase 2 was conducted prior to the IOT.
Electromagnetic Interference (EMI)/ Electromagnetic Compatibility (EMC)/ Electromagnetic Environmental Effects (E3) | Satisfactory | The Test Threat Support Package identified all threat targets and the required level of electronic warfare used during the IOT.
Radar Mode Characterization Test | Satisfactory | The record test consisted of[REDACTED] mission pulse iterations with one day separating the iterations. The live fire portion of the IOT focused on the ability of the sut equipped unit to detect threat representative rockets, artillery and mortars.

## Key
Test Data
Electronic Warfare (EW) Survivability
Electromagnetic Interference (EMI)/ Electromagnetic Compatibility (EMC)/ Electromagnetic Environmental Effects (E3)
Environmental Testing
Transportability/Mobility
Reliability Growth Demonstrations
Nuclear, Biological, Chemical Contamination Survivability (NBCCS)
Performance Testing
Army Interoperability Certification (AIC) Testing
Logistics Demonstration (LD) and Prognostics/Diagnostics Demonstration
Technical Publication Verification
Manpower and Personnel Integration (MANPRINT) Analysis Conference (MAC)
Software Qualification Test (SQT)
Software Independent Validation and Verification (IV&V)
Model and Simulation Verification
Logistics Demonstration Phase 2
Radar Mode Characterization Test
Cyber Security